## Executive Summary

A total of 6 equipment items were analyzed for Project A. The risk breakdown is as follows:

- High Risk: 1 item

- Medium Risk: 1 item

- Low Risk: 4 items

## Equipment Comparison Table

| Equipment Code | Equipment Name | P6 Due Date | Delivery Date | Variance (days) | Risk % | Risk Level | Manufacturing Country | Project Country |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 123458 | LV Switchgear - 400V/5000A Switchboard-3 (3-Sections) | 2026-02-27 | 2026-03-07 | 8 | 114.29% | High | Malaysia | Germany |
| 123457 | LV Switchgear - 400V/5000A Switchboard-2 (3-Sections) | 2026-02-25 | 2026-02-20 | -5 | -100.00% | Low | United Kingdom | Germany |
| 123456 | LV Switchgear - 400V/5000A Switchboard-1 (3-Sections) | 2026-02-21 | 2026-01-21 | -31 | -3100.00% | Low | India | Germany |
| 123457 | LV Switchgear - 400V/5000A Switchboard-2 (3-Sections) | 2026-02-25 | 2026-02-20 | -5 | -100.00% | Low | China | Germany |
| 123456 | LV Switchgear - 400V/5000A Switchboard-1 (3-Sections) | 2026-02-21 | 2026-01-21 | -31 | -3100.00% | Low | USA | Germany |
| 123457 | LV Switchgear - 400V/5000A Switchboard-2 (3-Sections) | 2026-02-25 | 2026-02-20 | -5 | -100.00% | Low | Philippines | Germany |

## High Risk Items

- LV Switchgear - 400V/5000A Switchboard-3 (3-Sections)

  - Equipment Code: 123458

  - P6 Due Date: 2026-02-27

  - Delivery Date: 2026-03-07

  - Variance (days): 8

  - Risk Percentage: 114.29%

  - Risk Level: High

  - Manufacturing Country: Malaysia

  - Project Country: Germany

  - Description: The delivery of this equipment is delayed by 8 days, which may impact the project timeline.

  - Factors Contributing to Variance: The delay is due to unforeseen manufacturing issues.

  - Potential Downstream Effects: The delay may cause a ripple effect, impacting other dependent tasks and the overall project schedule.

  - Recommended Mitigation Actions: Expedite shipping and closely monitor the delivery process.

## Medium Risk Items

- No medium risk items

## Low Risk Items

- LV Switchgear - 400V/5000A Switchboard-2 (3-Sections)

  - Equipment Code: 123457

  - P6 Due Date: 2026-02-25

  - Delivery Date: 2026-02-20

  - Variance (days): -5

  - Risk Percentage: -100.00%

  - Risk Level: Low

  - Manufacturing Country: United Kingdom

  - Project Country: Germany

  - Description: The delivery of this equipment is ahead of schedule by 5 days.

  - Factors Contributing to Variance: The early delivery is due to efficient manufacturing and logistics.

  - Potential Downstream Effects: The early delivery may provide a buffer for potential future delays.

  - Recommended Mitigation Actions: Continue to monitor the delivery process to ensure timely arrival.

## On-Track Items

- No on-track items

## Recommendations

- For high-risk items, expedite shipping and closely monitor the delivery process.

- For low-risk items, continue to monitor the delivery process to ensure timely arrival.

- Regularly review and update the project schedule to reflect any changes in equipment delivery dates.